## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Event Recommendation System
PROJECT SPONSOR | Cloud Counselage
PROJECT MANAGER | Jayanth G S
EXPECTED START DATE | 2020-06-15
EXPECTED COMPLETION DATE | 2020-07-31
ESTIMATED COST | Free resources used. So zero, for development.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | To buid an employee recommendation system which can be used by employees and interns of Cloud Counselage Pvt. Ltd.
BUSINESS CASE | One often misses events of interest sheerly due to a lack of awareness at the right time. Cloud Counselage also receives invites for events in multiple domains that need to be forwarded to people with relevant interests. The aim is to create a Recommender System that recommends only relevant events to each employee and intern based on their preferences, whenever the company receives invites for said events. The system should read new events and autonomously classify them into various domains. It should then match the event with all of those in the company database who have given said domains as a preference. Finally, for each event, the system should output the list of people whose preferences match with the event’s detected domain. Create a report documenting your approach and methodology followed.
GOALS/METRICS | As per the problem statement: The system should handle I/O only as mentioned in order to be evaluated correctly. Submission of the complete working code of the designed system to be done.
EXPECTED DELIVERABLES | Python Code, I/P and O/P results, Project Management documents
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | Code as per the problem statement using only Machine Learning and Deep Learning techniques. Suitable documentation.
OUTSIDE OF SCOPE | Actual deployment of the code on company's website
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Aditya Sangle
SUPPORT RESOURCES | Anaconda, Python 3.6, Jupyter Notebook,Google Colab, MS Office for documentation
SPECIAL NEEDS | Reports and Development logs to be maintained
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Aditya Sangle
KEY STAKEHOLDERS | Jayanth G S
END CUSTOMER | CC Employees and Interns
EXPECTED BENEFIT | Better recommendations on website, better workflow
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Lack of proper training data set, Model efficiency average.Getting more data to improve model performance.
ASSUMPTIONS | Will run suitably with the right model and inputs.
CONSTRAINTS | Lack of team members/No team members to build an efficient data set.